## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | AI/ML Engineer | 2025-12-07 | Whitespace in loan_status column | Sprint 1 | AI/ML Engineer | Logical | Trimmed values during preprocessing | 2025-12-09 | Closed | Dataset contained leading and trailing whitespaces in categorical values which caused label inconsistency during model training. Issue was resolved by applying string normalization in the preprocessing pipeline.
2 | AI/ML Engineer | 2025-12-09 | SHAP compatibility error | Sprint 1 | AI/ML Engineer | Logical | Updated SHAP explainer logic | 2025-12-11 | Closed | SHAP TreeExplainer raised compatibility errors with the trained XGBoost model. The explainer configuration was adjusted to match the model structure, resolving the issue successfully.
3 | Backend Developer | 2025-12-11 | Model prediction label mismatch | Sprint 1 | AI/ML Engineer | Logical | Corrected target label encoding | 2025-12-13 | Closed | Prediction failed due to mismatch between string-based labels and numeric model expectations. Proper label encoding was implemented consistently across training and inference stages.
4 | Full Stack Developer | 2025-12-13 | PDF report generation failure | Sprint 1 | Backend Developer | User Interface | Fixed data binding and layout logic | 2025-12-15 | Closed | PDF generation failed during runtime due to missing field validation. Input checks were added and report layout was corrected to ensure stable report generation.
5 | Chatbot Developer | 2025-12-15 | Chatbot FAQ response not triggered | Sprint 1 | Full Stack Developer | User Interface | Corrected intent mapping logic | 2025-12-27 | Closed | Chatbot was not triggering predefined FAQ responses due to incorrect keyword-to-intent mapping. The logic was corrected and validated with multiple test queries.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others